## Sheet1
Capstone Project
Milestone | Activity | SubTask | Suggestions | Owner | Column1 | Column2 | Column3 | Column4 | Column5
Milestone 1 | 1. Define the Problem and Get the Data, Explore (Data Report) |  |  | Devanandh
40 marks |  | Understand the features and describe them | Use common naming conventions | Devanandh
Due Date: March 3rd |  | Describe the problem statement | house_df | Devanandh
train
validate
test
2. EDA and Pre-processing (Feature engineering and selection)
|  | Eyeball the data | Work together as a team | Karan & Prabakaran
|  | Descriptive stats |  | Karan & Prabakaran
|  | data visualizations |  | Karan & Prabakaran
|  | Missing value treatment |  | Devanandh
|  | Outlier treatment | Collaborate in GitHub | Devanandh
Have discussions and whatsapp catchups
| 3. Modelling (Focus on accuracy and generalization) |  | Reach out to me any queries
|  | train, validate and test |  | Devanandh
|  | try different regression algorithms | Feb 24th | 1 algorithm per person
|  | check accuracy |  | 1 algorithm per person
|  | feature importance |  | 1 algorithm per person
|  | Interim Report |  | Merge report - Devanandh
|  | Jupyter Notebook | Review on March 1st - 9 pm. Please creat zoom - Prabakaran | [6 empty] | Dataframe name | X_name | y_name | Train | Test | Train_labels | Test_labels
Milestone 2 | 4. Evaluation of your model (Comparison of different models, performance tuning) |  |  | Outlier Strategy 3 - Outlier imputer through median approach (for high qty entries) along with related measures |  | 2019-03-11 | Prabhakaran/Devanandh/Karan |  |  | house_df_out3
60 marks |  | Hyperparameter tuning | Regression Models | Base model (without outlier treatment & regularization/standardization) (70/30) - LR,DTR,RFR |  | 2019-03-12 | LR- Karan DTR- Deva RFR - Prabhakaran |  | house_df_new-> | house_df_base | X_base | y_base | train_base | test_base | train_labels_base | test_labels_base
Due Date: Will be posted |  | Regularization | Eg: Linear Regression | Standardization & outlier treatment - model acc - LR,DTR,RFR |  | 2019-03-13 | LR- Prabhakaran DTR- Karan RFR - Deva | Zoom meeting - 9 to 10pm | house_df_out1-> house_df_out_2-> house_df_out3-> | house_df_scaled_out1 house_df_scaled_out2 house_df_scaled_out3 | X_scaled | y_scaled | train_scaled | test_scaled | train_labels_scaled | test_labels_scaled
|  | Model selection | Decision Tree Regression | PCA with std data - acc -- LR,DTR,RFR |  | 2019-03-14 | LR- Deva DTR- Prabhakaran RFR - Karan | Zoom meeting - 9 to 10pm | house_df_scaled3-> | house_df_pca | X_pca | y_pca | train_pca | test_pca | train_labels_pca | test_labels_pca
|  |  | Random Forest Regression | Ensemble techniques - Gradientboosting,Bagging, Adaboost, |  | 2019-03-15
|  |  | Ensemble Techniques | Model split-train,validate& test 40/30/30 | Hyperparameter tuning | 2019-03-16
|  |  | HyperParameter - RandomSearchCV, GridSearchCV | k fold validation | Hyperparameter tuning | 2019-03-16
| 5. Model deployment |  | KNN regression | CV tuning/random and grid search | Hyperparameter tuning | 2019-03-16
Productionizing model
Pickle deployment
6. Presentation and report
Create a detailed final report
present it